## LongTerm
Tasks	Deadline	Status	Comments
Finish converting models	April 31st	Done	This task was completed on time
Create Dashboard	April 31st	Done	This task was delayed, and was carried over to this term which was undesirable
Refactor codebase	May 21st	Done	This task was delayed
Implement 4 Features	July 31st	Ongoing
Run real life problems	October 31st	Pending
Implement Features	November 31st	Pending
Prepare for Symposium	February 1st	Pending

## ShortTerm
Tasks	Deadline	Status	Assignee	Comments
Refactoring	May 21st		Atulan, Ming-Ho, Joseph	Completed with delay
Implement Incremental solving	June 30th	Delayed	Chris, Ming-Ho	Completed with bugs
Implement Concurrent Solving	July 15th	Ongoing	Joseph, Chris	Pending
Implement SMT solver	July 30th	Ongoing	Atulan, Ming-Ho	Pending